## Close_Checklist
Day | Workstream | Task | Owner | Dependency | Status | Evidence | Comment
WD+1 | Integrity | Confirm posting periods, interfaces, bank imports, master data and tax setup | R2R Lead | - | Complete | 01_Integrity/2026-02_Integrity_Check.xlsx | Prerequisites reviewed
WD+1 | Reports | Run core AR/AP/Bank/GL/VAT reports for 2026-02 | Process Owners | Integrity complete | Complete | 02_Reports/2026-02_ERP_Report_Run_List.xlsx | All critical reports extracted
WD+2 | AR | Review aging, open items and unapplied cash | AR Analyst | Reports run | Complete | 03_Tieouts/2026-02_Core_Tieouts.xlsx | No material AR tie-out difference
WD+2 | AP | Review vendor open items, due items, parked/blocked invoices | AP Analyst | Reports run | Complete | 04_Issues/2026-02_Issue_Log.xlsx | 1 parked invoice remains operational pending
WD+2 | Treasury | Complete bank reconciliation and unmatched item review | Treasury | Bank statements imported | Complete | 03_Tieouts/2026-02_Core_Tieouts.xlsx | Bank fee JE posted
WD+3 | R2R | Review TB, manual JEs, accruals and balance support | GL Accountant | Tie-outs performed | Complete | 05_JE/2026-02_JE_Log.xlsx | All 6 JEs supported
WD+3 | Tax | Complete VAT ledger vs GL tie-out and exception review | Tax Accountant | GL detail available | Complete | 03_Tieouts/2026-02_Core_Tieouts.xlsx | VAT mismatch resolved via JE-004
WD+4 | Issues | Update issue log, confirm resolution and residual pending items | Finance Manager | All workstreams updated | Complete | 04_Issues/2026-02_Issue_Log.xlsx | 5 closed / 1 pending non-blocking
WD+4 | Close | Prepare pending items memo and signoff pack | R2R Lead | Issues updated | Complete | 07_Pending/2026-02_Pending_Items_Memo.md; 08_Signoff/2026-02_Signoff_Memo.md | Pack ready for reviewer
WD+5 | Signoff | Final controller review and formal signoff | Finance Manager | Pack ready | Pending | 08_Signoff/2026-02_Signoff_Memo.md | Pending signature only

## Summary
Metric | Value
Total tasks | 10
Complete | 9
Pending | 1
Close readiness | Ready for signoff